## S-Curve Data
Week | Week Start | Week End | Planned Cumulative % | Target Milestone
1 | 2026-06-10 | 2026-06-16 | 0.1 | Setup
2 | 2026-06-17 | 2026-06-23 | 0.25 | MST
3 | 2026-06-24 | 2026-06-30 | 0.45 | INV
4 | 2026-07-01 | 2026-07-07 | 0.65 | SLS
5 | 2026-07-08 | 2026-07-14 | 0.85 | FIN
6 | 2026-07-15 | 2026-07-21 | 1 | UAT

## Milestone Plan
Phase | Modul | Milestone | Start Date | End Date | Planned Weight % | Dependency | Exit Criteria
Phase 0 | ALL | Setup repo, staging, dan environment | 2026-06-10 | 2026-06-16 | 0.1 | Kickoff | Environment ready
Phase 1 | MST | Master Data Marketplace (Seller, Buyer, Product) | 2026-06-17 | 2026-06-23 | 0.15 | Phase 0 | Database master ready
Phase 2 | INV | Katalog & Stok Barang | 2026-06-24 | 2026-06-30 | 0.2 | Phase 1 | Stok terintegrasi
Phase 4 | SLS | Checkout Transaksi & Cart | 2026-07-01 | 2026-07-07 | 0.25 | Phase 2 | Checkout flows working
Phase 6 | FIN | Payment Gateway Integration & Wallet | 2026-07-08 | 2026-07-14 | 0.2 | Phase 4 | Pembayaran valid
Phase 9 | ADM | Admin Moderasi & UAT | 2026-07-15 | 2026-07-21 | 0.1 | Phase 6 | Sign-off

## Developer Task Board
Task ID | Epic / Modul | Feature | Task Name | Deskripsi Task | Notes | Priority | Tipe Task | Ref 3.2 | Ref 4 / FR Code | Acceptance Criteria Checklist | Blocker | Sprint Target
TASK-MST-001 | MST | Master Merchant | CRUD Merchant Account | Build merchant registration, profiles API and frontend views | Must support file upload for merchant documents | High | Full Stack |  |  | 1. Reg form works 2. Profile edit works
TASK-MST-002 | MST | Master Product | Product Catalog CRUD | Build seller product catalog dashboard & details page |  | High | Full Stack |  |  | 1. Multi images upload 2. Price validation
TASK-INV-001 | INV | Stock Reservation | Real-time Stock Updates | Decrease product stock count during checkout cart reservation |  | High | Backend |  |  | 1. Database isolation locks
TASK-SLS-001 | SLS | Cart Checkout | Checkout Process with Voucher | Implement checkout transaction calculation with voucher discount apply |  | High | Full Stack |  |  | 1. Diskon percentage correct 2. Min purchase checked
TASK-FIN-001 | FIN | Payment Gateway | Midtrans Payment Integration | Connect system payment triggers to Midtrans sandbox SNAP API |  | High | Backend |  |  | 1. Callback notification handler 2. Expiry works
TASK-ADM-001 | ADM | Moderation Control | Merchant Verification Portal | Admin panel screen for viewing, accepting or rejecting new merchants |  | Medium | Frontend |  |  | 1. Direct verification status update

## QA Test Cases
TC ID | Module | Scenario | Test Steps | Expected Result | Status | ERP Role
TC-MST-001 | MST | Registrasi merchant dengan email valid | 1. Buka registrasi seller 2. Isi form lengkap 3. Klik submit | Akun merchant terbuat dengan status 'pending' | Active | user
TC-SLS-001 | SLS | Checkout dengan keranjang kosong | 1. Klik keranjang belanja kosong 2. Klik tombol checkout | Tombol checkout disabled dan muncul error toast | Active | user